## Feuille 1
| Feature | Action | Expected result | Observed result
1 | A home page showing (dynamically) all products available for sale | Open the home page on a browser. | Display all the products | OK / Error description: "Error! Check if server is up and running"
2 | A product page showing details about the selected product. | Click on one of the products in the homepage. | Opens a page in a new tab where the selected product is displayed with details about it. As well as the price of the product and options for selecting colors and quantity. There is also a "add to card button". | OK / Product page is not avalible is server is not running.
3 | From the product page users will be able to select the required quantity and colour and then add the product to the cart. Part 1/3 | Click on the "Please, select a color" in the product page. | Opens a dropdown menu where user can choose the color. | OK / Error description: "Error! Check if server is up and running" / In case there is no color selected: "Product color has not been selected, please pick a color"
4 | From the product page users will be able to select the required quantity and colour and then add the product to the cart. Part 2/3 | Click on the field dedicated to "Number of articles (1-100):" | User can type in numbers(only) or use the arrow keys to change the quantity of the product. | OK / In case user trying to enter "0": "Cannot add "0" articles to the cart, please select a valid value"
5 | From the product page users will be able to select the required quantity and colour and then add the product to the cart. Part 3/3 | Click on the "Add to cart button" | The product'll be saved in the cart with the choosen color and quantity. (If the user clicks the "Add to cart button" muliple times for the same color, the product should show up in the cart page only once but the quantity should be respective to the total items added to the cart.) | OK
6 | A cart page showing (dynamically) all products seleceted previously. | Open the cart page on a browser. | Displays the items that has been previously selected as well as the total price for the items(dynamycally). | OK / Error description: "Error! Check if server is up and running"
7 | User can modify the quantity or delete products completely from the cart. | Changing the field dedicated to "Qty:" or the "Delete" button. | The "Total" section updates respectively and in case clicking the "Delete" button the item also disappears from the list in the cart. | OK / This option is not avalible if the server is down.
8 | Leaving the cart page, should not remove the items from the cart. | Refreshing or changing the page. | Displays the items that has been previously selected as well as the total price for the items(dynamycally). | OK / Error description: "Error! Check if server is up and running" - If the server is down non of the selected products shown in the cart, however if the server is restored, refreshing the page will load the products from local storage.
9 | A form to be submitted in order to confirm the order. Part 1/2 | Filling the form. | Display no error message. | OK / Display an error message, for example: "You have entered an invalid email format!"
10 | A form to be submitted in order to confirm the order. Part 2/2 | Clicking the "Order!" button. | If the form was filled correctly, opens conformation page and delete items from the cart. | OK / If the form was filled incorrectly, error messages will show under each form field with incorrect information.
11 | Confirmation page showing the user’s order number sent by the API. | Clicking the "Order!" button. | Thanking the user for the order and displaying the confirmation number. This number must be not stored anywhere. | OK / Error description: "Error! Check if server is up and running"
12
13
14
15